## Team Info
Team members
1 | Divyashree M D | DMD
2 | Akshay Kumar K | AK
3 | Dheeraj B N | DBM
4 | Varshitha J | VJ
5 | Rachamadugu Sanjay Guptha | RSG
6 | Banapili Saikumar | BSK
7 | Archies Singh | AS
8 | Mihir Kumar | MK
9 | Pranav Pandey | PP

## Iteration (Sprint) Backlog
Sprint-1 Backlog
day 0 = initial estimate
Requirement | Task ID | Task Description | Responsible | Cum. Hours Spent | Status (Not Started / In Progress / Completed) | Hours of work remaining until completion
[7 empty] | Thu | Fri | Mon | Tue | Wed | Thu | In Progress
[6 empty] | Day | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2023-03-30 | Not Started
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | Carry Over
|  |  | Team | 0 |  | 319 | 38 | 52 | 62 | 0 | 0 | 0 | Completed
REQ1 - Login |  |  | RSG
UI of employee login page | REQ1_T1 |  | MK |  | Completed | 4 |  | 2
Client-side validation of user entered information | REQ1_T2 |  | AS |  | Completed | 3 |  | 2 | 2
Creating a session | REQ1_T3 |  | AS |  | Carry Over | 5
Role-based Dashboard Rendering | REQ1_T4 |  | MK |  |  | 8
Configuring Azure DevOps Organization | REQ1_T5 |  | PP |  |  | 4
Backend Login Validation Logic | REQ1_T6 |  | SG |  | Completed | 12 | 8 | 4
Server-side validation of user entered information | REQ1_T7 |  | SG |  | Completed | 12 |  | 4 | 4
Role-based Dashboard Rendering | REQ1_T8 |  | SG |  | In Progress | 12 |  |  | 4
Exception Handling | REQ1_T9 |  | SG |  | Not Started | 4
Unit Tests | REQ1_T10 |  | SG |  | Not Started | 4
REQ2- Admin
Designing UI for Admin Dashboard | REQ2_T1 |  | AS |  | In Progress | 10 |  |  | 6
Designing UI for verification of booked seat by scanning QR code | REQ2_T2 |  | AS |  |  | 4
Designing UI for Managing the records | REQ2_T3 |  | AS/MK |  |  | 5
Registering new Employee | REQ2_T4 |  | AK |  | Completed | 12 | 4 | 6
Exception Handling for new employee registration | REQ2_T5 |  | AK |  | In Progress | 4 | 2 |  | 2
Unit Tests for new employee registration | REQ2_T6 |  | AK |  | In Progress | 6 |  | 2
Verification of booked seat | REQ2_T7 |  | AK |  | In Progress | 9 |  |  | 6
Exception Handling for Verification of booked seat | REQ2_T8 |  | AK |  | In Progress | 8
Unit Tests for Verification of booked seat | REQ2_T9 |  | AK |  | Not Started | 4
Sending a mail to a registered employee | REQ2_T10 |  | AK |  | In Progress | 10 | 2
Adding Floors and Seats | REQ2_T11 |  | BSK |  | In Progress | 12 | 5 | 3 | 4
Unit Tests for Adding Floors and Seats | REQ2_T12 |  | BSK |  | Not Started | 12
Exception Handling for Adding Floors and Seats | REQ2_T13 |  | BSK |  | In Progress | 10 | 3 | 5 | 4
REQ3-Employee
Designing UI for Seat booking | REQ3_T1 |  | AS/MK |  | In Progress | 8 |  |  | 6
Designing UI for User Dashboard | REQ3_T2 |  | MK |  |  | 8
Designing UI for rendering seat booking QR code | REQ3_T3 |  | MK |  |  | 2
Backend Implementation for retrieving required information for the User Dashboard | REQ3_T4 |  | VJ |  | Completed | 12 | 4 | 8
Unit Tests for retrieving required information for the User Dashboard | REQ3_T5 |  | VJ |  | Not Started | 4
Exception Handling for retrieving required information for the User Dashboard | REQ3_T6 |  | VJ |  | Not Started | 8
Backend Implementation of Seat booking logic | REQ3_T7 |  | DMD |  | Completed | 25 | 5 | 8 | 8
Unit Tests for Implementation of Seat booking logic | REQ3_T8 |  | DMD |  | Not Started | 8
Exception Handling for Implementation of Seat booking logic | REQ3_T9 |  | DMD |  | Not Started | 4
Backend Implementation for retrieving required information for the User Profile | REQ3_T10 |  | VJ |  | In Progress | 12 |  |  | 8
Unit Tests for retrieving required information for the User Profile | REQ3_T11 |  | VJ |  | Not Started | 4
Exception Handling for retrieving required information for the User Profile | REQ3_T12 |  | VJ |  | Not Started | 8
REQ4-Configuring Mail Service
Configuring the mail service | REQ4_T1 |  | DBN |  | Completed | 12 | 3 | 5 | 4
Unit Tests for Mail Service | REQ4_T2 |  | DBN |  | Not Started | 4
Exception Handling for Mail Service | REQ4_T3 |  | DBN |  | Not Started | 8
Building customised mail template for different mails | REQ4_T4 |  | DBN |  | In Progress | 10 | 2 | 3 | 4
REQ5-DevOps
Configuring Azure DevOps Organisation for the project | REQ5_T1 |  | PP |  | In Progress | 6
Integrating the codebase with Azure Pipelines | REQ5_T2 |  | PP |  | Not Started | 2
REQ6-Unplanned |  |  |  | 0
Continuous Integration | REQ6_T1 |  | PP |  | Not Started
Continuous Deployment | REQ6_T2 |  | PP |  | Not Started
0
Total(IE) hours available for Spint-1 | 432
Total hours estimated for Sprint-1 | 319

## Planned Leaves
Team Member | Thu | Fri | Mon | Tue | Wed | Thu
| 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2023-03-30 | Leave
| 1 | 2 | 3 | 4 | 5 | 6 | On Duty
Divyashree M D | [6 empty] | Holiday
Akshay Kumar K | [6 empty] | Half Day
Dheeraj B N
Varshitha J
Rachamadugu Sanjay Guptha
Banapili Saikumar
Archies Singh
Mihir Kumar
Pranav Pandey

## Idealized Burndown
Idealized Line | day: | 0 | 6
| Planned | 319 | 0
| Remaining | 319

## Release Plan
Sprint-1 Release
Iteration Release | Date | Project | Release Type | Release Features | Open Issues
| 2023-03-30 | SSB
SSB

## Metrics
# | Start Date | End Date | Estimated Hrs | Actual Hrs (Planned + Unplanned) | Effort Deviation | Tasks Planned | Tasks Completed | Scope Coverage | Remarks
| 2023-03-23 | 2023-03-30 | 319 | 0 | -100