## Sheet1
OPEN vs. CLOSED ISSUE TRACKER
| # | ISSUE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
| 1 | mail not sent | medium | 2023-03-24 | dheeraj | 2023-03-31 | Dheeraj | Dependency change
| 2 | dynamic value for email | high | 2023-04-05 | dheeraj | 2023-04-06 | Dheeraj | configration Database
| 3 | authorization | high | 2023-03-31 | Sanjay | 2023-04-03 | sanjay
| 4 | swagger authroization | high | 2023-04-04 | sanjay | 2023-04-04 | sanjay
| 5 | bean Rowmapper issue | medium | 2023-04-03 | sai kumar | 2023-04-05 | sai kumar
| 6 | limited access credicts for devops | high | 2023-03-24 | Pranav | 2023-03-27 | Pranav
| 7 | connection to shared Db | high | 2023-03-24 | Team | 2023-03-24 | Team
| 8 | code conflit | high | 2023-03-27 | akshay | 2023-03-27 | akshay
| 9 | code conflit | high | 2023-03-28 | varshitha | 2023-03-28 | varshitha
| 10 | code conflit | high | 2023-04-01 | varshitha | 2023-04-01 | varshitha
| 11 | code conflit | high | 2023-04-03 | varshitha | 2023-04-03 | varshitha
| 12 | code conflit | high | 2023-03-31 | divya | 2023-03-31 | divya
| 13 | Kubernetes | low | 2023-04-03 | Pranav
| 14 | null retruing in sql query | high | 2023-04-06 | varshitha | 2023-04-06 | divya
| 15 | Mail authention from new mail | high | 2023-04-06 | dheeraj | 2023-04-07 | Dheeraj
| 16 | Integration of backend to react | high | 2023-03-31 | Sanjay | 2023-04-01 | Sanjay
| 17 | code conflit | high | 2023-04-04 | sai kumar | 2023-04-04 | sai kumar
| 18 | Qr code not genrated for string more than 10 | high | 2023-03-24 | mihir | 2023-03-25 | mihir
| 19 | seat booking matrix | medium | 2023-03-27 | mihir | 2023-03-27 | mihir
| 20 | seat booking functionality | high | 2023-03-28 | mihir | 2023-04-04 | mihir
| 21 | date selection type | high | 2023-03-27 | mihir | 2023-03-28 | mihir
| 22 | Integration problem getting html page | high | 2023-03-28 | mihir | 2023-03-30 | sanjay
| 23 | integration from frontend to backend | high | 2023-03-28 | mihir | 2023-04-04 | team
| 24 | null pointer /api/employee/next/booked/deatails | high | 2023-04-06 | mihir | 2023-04-06 | mihir
| 25 | entity change issue with constructor | high | 2023-04-03 | dheeraj | 2023-04-03 | Dheeraj
| 26 | editing date format | high | 2023-06-06 | archies |  | archies
| 27 | qr scanning | medium | 2023-03-31 | archies | 2023-04-01 | archies
| 28 | login logic | high | 2023-04-07 | archies | 2023-04-07 | archies
| 29 | Writing select statements returing null | high | 2023-03-29 | divya | 2023-03-30 | divya
| 30 | sms auth token expiry | high | 2023-04-04 | akshay | 2023-04-04 | akshay
31
32
33
34
35
36
37
38