## Sprint-4.0 Retrospection
Project Name: SSB (Secure Seat Booking)
Sprint - 2.0 |  | Date: 07-April-2023
# | +ve | r | Action Item | Target Date | Responsible
1 | Backend API’s logic went well as per plan, no carry over for release. | Integrating react with backend for all pages | Time constraints |  | Archies Singh/ Mihir Kumar
2 | high priority Unplanned tasks are completed | Releasing seat status with respect to employee booked shift end time | Time constraints |  | Backend Team
3 | Proper work structure followed in the sprint
4 | More knowledge on technology.
5 | Proper coding standards
6 | SMS and mail service configured in application
7 | Using previous seat booking details for booking current seat feature working in backend
8 | Modification of seat booking feature in backend
9 | JWT tocken for authorization and integrated in react