## Sprint-4.0 Retrospection
Project Name: SSB (Secure Seat Booking)
Sprint - 1.0 |  | Date: 30-March-2023
# | +ve | r | Action Item | Target Date | Responsible
1 | Backend API’s logic went well as per plan, no carry over for successive sprint. | Integrating react with backend for authorization was failed | Use JWT Token for Authorization | 31-March-2022 (Sprint - 2.0) | Sanjay Gupta
2 | Used of DAO class effectively to build complex SQL query using JOINS. | Proper time for daily Scrum have not followed | Reinitiate the proper scrum meeting time | 31-March-2022 (Sprint - 2.0) | Akshay Kumar
3 | Unplanned tasks are completed | Retrieving of current available seats in react | Do more R&D for betterment of Project
4 | Kubernetes networking part worked as intended | Avoid Code conflict while using Git.
5 | Seat booking validation for selecting dates archived in front-end
6 | Team work and coordination.
7 | Proper work structure followed through the sprint
8 | More knowledge on technology.
9 | Proper coding standards